## Sheet1
Ilham Buono Putra, Universitas Bhayangkara Jakarta Raya, Informatika, ID Agate: 100
Schedule produksi untuk game Tik-tok Pong dalam waktu 4 minggu dan anggota timnya sesuai dengan anggota tim kamu pada studi independen ini.
Timeline Production Game - Tik-tok Pong
Tahap | Task Overview | Keterangan | Pre-Production | [6 empty] | Sprint 1 | [13 empty] | Sprint 2
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
Pre-Production | Brainstorm Concept
Gameflow
Art Direction
Game design Document
Feature Development | Core Game | bar: Sprint 1 Day 8 to Sprint 1 Day 11
Balancing | bar: Sprint 1 Day 12 to Sprint 1 Day 14
History Last Turn | bar: Sprint 1 Day 15
Change Theme | bar: Sprint 1 Day 15 to Sprint 1 Day 21
Leaderboard | bar: Sprint 1 Day 16
Option In Game | bar: Sprint 1 Day 17
Hosting Game | bar: Sprint 1 Day 18 to Sprint 1 Day 21
Asset Development | In Game Asset | bar: Sprint 2 Day 22 to Sprint 2 Day 23
UI | bar: Sprint 2 Day 24 to Sprint 2 Day 25
Sound | bar: Sprint 2 Day 26
Operational Support | Hosting Server | bar: Sprint 2 Day 27 to Sprint 2 Day 28
Testing Period | Usability Testing | bar: Sprint 2 Day 26 to Sprint 2 Day 27
Integration Testing | bar: Sprint 2 Day 28 to Sprint 2 Day 29
Final Adjustment | bar: Sprint 2 Day 29 to Sprint 2 Day 30
Development & maintenance | Project Handoff | bar: Sprint 2 Day 29 to Sprint 2 Day 30
Producer
Designer
Programmer
Artist
Tester

## Sheet3
Tahap | Task Overview | Keterangan | Pre-Production | Sprint 1 |  |  |  | Sprint 2
|  |  | Week 1 | Week 2 | Week 3 |  | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Pre-Production | Brainstorm Concept
Gameflow
Art Direction
Game design Document
Feature Development | Core Game
| Balancing |  |  |  |  | .
Equipment
Theme
Combat
Option In Game
Asset Development | In Game Asset
UI
Sound
Operational Support | Device Optimization
Testing Period | Usability Testing
Integration Testing
Final Adjustment
Development & maintenance | Project Handoff
Producer
Designer
Programmer
Artist
Tester
Product Manager